## Deployment History
Product | Client | Issue | Issue Date | Description | Development Process | Current Status | Moved to Testing | Moved to Testing By | Moved to Testing Date & Time | Testing Completed | Testing Completed By | Testing Completed Date & Time | Delivery Date | Delivered By | Version | Created By | Created Date & Time | Last Modified By | Last Modified Date & Time
OLMS | Client A | OLMS-101 | 2026-08-01 | Order status not updating after dispatch | Code changes completed for dispatch status sync | Testing Completed | Yes | Employee A | 2026-08-10 14:32 | Yes | Employee B | 2026-08-15 11:05 | 2026-08-20 | Employee B | v2.4.1 | Employee A | 2026-08-01 09:15 | Employee B | 2026-08-20 17:40
OLMS | Client B | OLMS-102 | 2026-08-05 | Add bulk upload for stock entries | In progress - backend API in review | Development In Progress | No |  |  | No | [5 empty] | Employee A | 2026-08-05 10:00 | Employee A | 2026-08-05 10:00

## Activity History
Deployment ID | Product | Client | Issue | Action | Previous Status | New Status | Remarks | Changed By | Changed Date & Time
OLMS-101 | OLMS | Client A | OLMS-101 | Created | - | New |  | Employee A | 2026-08-01 09:15
OLMS-101 | OLMS | Client A | OLMS-101 | Status Changed | New | Development In Progress |  | Employee A | 2026-08-02 11:15
OLMS-101 | OLMS | Client A | OLMS-101 | Moved to Testing | Development Completed | Moved to Testing |  | Employee A | 2026-08-10 14:32
OLMS-101 | OLMS | Client A | OLMS-101 | Reopened | Testing In Progress | Development In Progress | Bug in dispatch status sync found during QA | Employee B | 2026-08-12 16:10
OLMS-101 | OLMS | Client A | OLMS-101 | Status Changed | Development In Progress | Development Completed | Fix verified locally | Employee A | 2026-08-13 10:05
OLMS-101 | OLMS | Client A | OLMS-101 | Moved to Testing | Development Completed | Moved to Testing | Re-test after fix | Employee A | 2026-08-13 10:30
OLMS-101 | OLMS | Client A | OLMS-101 | Testing Completed | Testing In Progress | Testing Completed | Verified on staging, fix confirmed | Employee B | 2026-08-15 11:05
OLMS-101 | OLMS | Client A | OLMS-101 | Delivered | Ready for Delivery | Delivered |  | Employee B | 2026-08-20 17:40

## Legend & Notes
OLMS Product Deployment History — Export Format
Sheet 1 (Deployment History): one row per deployment record. Blue header columns are
entered by employees; orange header columns are system-generated audit fields and must
never be manually editable in the live application.
Sheet 2 (Activity History): append-only log — every status change, on every deployment
record, by every employee who touched it. Never deleted or overwritten, even when the
main record itself is edited later. This is the audit source of truth per Section 10.
Reopen path: testing can send a record back to development ('Reopened' action). The
main record's Moved to Testing / Testing Completed dates always reflect the MOST RECENT
test cycle; earlier cycles are only visible in this Activity History sheet, as shown in
the OLMS-101 sample rows below (reopened once, then re-tested and delivered).
Sample rows are illustrative only — replace or remove before real use.